## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: |  | Dr. David Chrisman |  |  | TEAM NAME: | Ville Students | [5 empty] | DOCUMENT HISTORY:
PROJECT SPONSOR: |  | Kim Dehler |  |  | PROJECT TITLE: | Blue Ridge Animal Rescue & Sanctuary Website | [5 empty] | Version | Issue Date | Changes
[12 empty] | [1.0] | 2023-01-23 | Addition of Requirements 1-62 and the features that could be currently identified for each.
REQUIREMENT INFORMATION | [5 empty] | RELATIONSHIP TRACEABILITY | [5 empty] | [1.1] | 2023-02-05 | Date fields added. Version Control section added and updated.
ID | TYPE | CATEGORY | REQUIREMENT | PRIORITY | STATUS | BUSINESS OBJECTIVE | DELIVERABLE(S) | VERFICATION | VALIDATION | DATE IDENTIFIED | DATE COMPLETED | [2.0] | 2023-04-01 | Updated requirements status, and removed/edited some according to client feedback.
SR0001 | Functional | Payment | The payment system shall allow donations to be collected. | High | In progress | Fund operations through donations | Implementing a payment system, with a donation button on the website that redirects users to the donation forms/page. | Test the donation feature on the website | Integration Test, Unit Test & User Acceptamce Test (UAT) - perform donation process. | 2023-01-23 | N/A | [2.1] | 2023-04-02 | Added completion dates for those requirements that have been met.
SR0002 | Functional | Payment | The payment system shall allow donations to be edited. | High | Incomplete | Fund operations through donations | Functional forms or a third-party system where donation amount can either be selected from a list, or where users can enter a custom amount. | Ensure ability to edit donations on the website. | UAT - donation amount and information can be edited on donation page before payment processing. | 2023-01-23 | N/A | [2.2] | 2023-04-03 | Removed requirements that the Project Sponsor deemed unnecessary or irrelevant.
SR0003 | Functional | Payment | The payment system shall allow donations to be deleted. | High | Incomplete | Protect donor information and keep accurate donation records | N/A, payment system that is implemented should contain an option that allows the admins to be able to delete records. | testa donations can be deleted from the database. | User (Admins) Testing - admins can remove (outdated) donation information. | 2023-01-23 | N/A
SR0004 | Functional | Payment | The payment system shall allow collection of adoption fee payments. | High | In progress | Fund operations through adoption fee payments | An adoption page where users are to pay an adoption fee through the implemented system. | Use website to test the collection of adoption fee payments. | Unit Test & UAT - Adoption page should request payment for adoption fee. | 2023-01-23 | N/A
SR0005 | Functional | Payment | The payment system shall allow editing of adoption fee payments. | High | Incomplete | Fund operations through adoption fee payments | N/A, payment system that is implemented should contain an option that allows the admins to be able to edit the amount charged. | Use website to test that adoption payments can be edited. | Unit Test & User (Admins) Testing - admins are able to edit adoption fee amount. | 2023-01-23 | N/A
SR0006 | Functional | Payment | The payment system shall allow deletion of adoption fee payments. | High | Incomplete | Protect adopter information and keep accurate payment records | N/A, payment system that is implemented should contain an option that allows the admins to be able to delete records. | Test that adoption payments can be deleted. | Unit Test & User (Admins) Testing - admins can delete (outdated) adoption fee transaction records. | 2023-01-23 | N/A
SR0007 | Functional | Payment | The support us page shall allow a link to an Amazon wishlist to be created. | Medium | Complete | Fund and support operations through wishlists and third party referral programs. | Website page with linked items for a wishlist must be created. | Test at the link to the Amazon list wish list launches and open the page. | Unit Test & UAT - links should redirect users to the specified pages. | 2023-01-23 | 2023-02-28
SR0008 | Functional | Payment | The support us page shall allow the Amazon wishlists to be edited. | Medium | Complete | Fund and support operations through wishlists and third party referral programs. | Add/Edit button should be created and added in the wishlist section. | test at the Amazon wish list can be edited from the website. | User (Admins) Testing - admins can edit the wishlist. | 2023-01-23 | 2023-02-28
SR0009 | Functional | Payment | The support us page shall allow wishlist items to be deleted. | Medium | Complete | Fund and support operations through wishlists and third party referral programs. | Delete button should be created and added to the wishlist section. | test that wish list items can be deleted. | User (Admins) Testing - admins can delete wishlist items. | 2023-01-23 | 2023-02-28
SR0010 | Functional | Database | The database shall allow for financial statements to be created. | Medium | Incomplete | Review organization's finances conveniently | Implement a third-party database that allows financial statements to be created by the admins. | Attempt to create several financial statements using the webpage. | Unit Test & User (Admins) Testing - admins can create financial statements. | 2023-01-23 | N/A
SR0011 | Functional | Database | The database shall allow for financial statements to be edited. | Medium | Incomplete | Review organization's finances conveniently | N/A, the third-party database should contain an option for editing the statements. | Edit two financial statements using website features. | Unit Test & User (Admins) Testing - admins can edit the financial statement. | 2023-01-23 | N/A
SR0012 | Functional | Database | The database shall allow for financial statements to be deleted. | Medium | Incomplete | Review organization's finances conveniently | N/A, the third-party database should contain an option for deleting the statements. | Test that financial statements can be permanently deleted. | Unit Test & User (Admins) Testing - admins can delete (outdated) statements. | 2023-01-23 | N/A
SR0013 | Functional | Volunteer | The website shall allow users to complete volunteer applications. | Medium | Complete | Acquire volunteers to support events and other business activities | A volunteer page should be created with a button that links to an application form. | Create several volunteer applications. | UAT - users can complete the volunteer forms. | 2023-01-23 | 2023-03-30
SR0014 | Functional | Volunteer | The website shall allow users to edit volunteer applications. | Medium | Complete | Acquire volunteers to support events and other business activities | A form/application submissions page should be created and an edit application button should be applied that allows for users to edit information. | Attempt to use webpage to write volunteer profiles. | UAT - users can edit their volunteer form information. | 2023-01-23 | 2023-03-30
SR0015 | Functional | Volunteer | The website shall allow users to delete volunteer applications. | Medium | Complete | Acquire volunteers to support events and other business activities | A delete button should be shown on both admin and user side on the submissions page to delete the application that was submitted, or for admins to delete an outdated application. | Delete five volunteer profiles successfully using the website. | Unit Test & User (Admins) Testing - admins can delete (outdated) volunteer application records. | 2023-01-23 | 2023-03-30
SR0016 | Functional | Adopt | The website shall allow users to complete adoption applications. | High | In progress | Facilitate adoption of animals | An adoption page should be created with an "adoption" button that redirects users to an adoption application form. | Use website to create several adoption applications. | Unit Test & UAT - website adoption button should take users to an application to fill out. | 2023-01-23 | N/A
SR0017 | Functional | Adopt | The website shall allow users to edit adoption applications. | High | In progress | Facilitate adoption of animals | A form/application submissions page should be created and an edit application button should be applied that allows for users to edit information. | Attempt to edit three adoption applications. | UAT - users are able to edit their information on the application form. | 2023-01-23 | N/A
SR0018 | Functional | Adopt | The website shall allow users to delete adoption applications. | High | In progress | Facilitate adoption of animals | A delete button should be shown on both admin and user side on the submissions page to delete the application that was submitted, or for admins to delete an outdated application. | Attempt to delete several adoption applications. | Unit Test & User (Admins) Testing - admins can delete (outdated) application forms | 2023-01-23 | N/A
SR0022 | Functional | Newsletter | The website shall allow a newsletter to be created. | Low | Complete | Keep stakeholders in the loop and facilitates recurring communication with website visitors | A page for newsletters should be created with codes for thumbnails for the newsletter cover and hyperlinked to the actual newsletter document. | Create several newsletters within the website. | Unit Test & User (Admins) Test - admins can create a newsletter to be added onto the website. | 2023-01-23 | 2023-03-01
SR0023 | Functional | Newsletter | The website shall allow a newsletter to be edited. | Low | Complete | Keep stakeholders in the loop and facilitates recurring communication with website visitors | N/A, this process should be done in the codes, where admins can edit the thumbnail and newsletter document. | Ensure that you can edit five newsletters on the website. | Unit Test & User (Admins) Testing - admins can edit a previously added newsletter. | 2023-01-23 | 2023-03-01
SR0024 | Functional | Newsletter | The website shall allow a newsletter to be deleted. | Low | Complete | Keep stakeholders in the loop and facilitates recurring communication with website visitors | N/A, this process should be done in the code, where admins can remove the thumbnail and newsletter document. | ensure that you can delete several newsletters on the website. | Unit Test & User (Admins) Testing - admins can delete (outdated) newsletter. | 2023-01-23 | 2023-03-01
SR0025 | Functional | Newsletter | The website shall allow a user to subscribe to the newsletter via email. | Low | Complete | Keep stakeholders in the loop and facilitates recurring communication with website visitors | On the page for newsletters and several other locations specified by the sponsor, a small form, button, or hyperlink for users to subscribe to a newsletter should be created. | Create a newsletter subscriptions within the website. | UAT - users of the website can subscribe and receive emails from the organization through the subscription. | 2023-01-23 | 2023-03-01
SR0026 | Functional | Newsletter | The website shall allow a user to unsubscribe to the newsletter via email. | Low | Complete | Keep stakeholders in the loop and facilitates recurring communication with website visitors | On the page for newsletters and several other locations specified by the sponsor, a small form, button, or hyperlink for users to unsubscribe to a newsletter should be created. | Edit newsletter subscriptions on the website. | UAT - users can unsubscribe from the mailing list and stop receiving communications from the organization. | 2023-01-23 | 2023-03-01
SR0027 | Functional | Contact | The website shall provide contact/social media information. | Low | Complete | Allows website visitors to contact rescue staff and view social media platforms | A contact page should be created and on specified locations of the website, hyperlinks for contact methods, such as social media, should be created. | Access social media and contact information on the website. | Unit Test & User (Admins) Test - admins can create a contact information on the webpage, and linked social media accounts should redirect to the specified website. | 2023-01-23 | 2023-02-28
SR0028 | Functional | Contact | The website shall allow editing of contact/social media information. | Low | Complete | Allows website visitors to contact rescue staff and view social media platforms | N/A, this process is done in the codes, where admins/developers can change the linked page/contact form. | Edit the social media and contact information on the website. | Unit Test & User (Admins) Test - admins can edit their contact information on the webpage. | 2023-01-23 | 2023-02-28
SR0029 | Functional | Contact | The website shall allow deletion of contact/social media information. | Low | Complete | Allows website visitors to contact rescue staff and view social media platforms | N/A, this process is done in the codes where admins/developers remove (ourdate) contact methods and hyperlinks. | Attempt to delete contacts and social media information off the website. | Unit Test & User (Admins) Test - admins can delete (outdated) contact information on the webpage. | 2023-01-23 | 2023-02-28
SR0030 | Functional | Events | The website shall allow for an event calendar to be created. | Low | Complete | Advertise upcoming events to website visitors | An event page should be created and a calendar widget can be created. | Attempt to create an event calendar on the website. | Unit Test & User (Admins) Test - admins can create events to be added onto the calendar. | 2023-01-23 | 2023-03-05
SR0031 | Functional | Events | The website shall allow for an event calendar to be edited. | Low | Complete | Advertise upcoming events to website visitors | Add/Edit button should be created and added in the calendar section. | edit an event calendar on the website. | Unit Test & User (Admins) Testing - admins can edit calendar events. | 2023-01-23 | 2023-03-05
SR0032 | Functional | Events | The website shall allow for an event calendar to be deleted. | Low | Complete | Advertise upcoming events to website visitors | Delete button should be created and added to the calendar section. | Delete five event calendars off of the website. | Unit Test & User (Admins) Testing - admins can delete (outdated) events on the calendar. | 2023-01-23 | 2023-03-05
SR0033 | Functional | Resource | The website shall allow for photos to be uploaded. | High | Complete | Allows website visitors to photos of the animals and may help encourage adoption | An easy gallery or sections for photos on the website accessible to the admins only. | Attempt to upload photos on the website. | Unit Test & User (Admins) Testing - admins can add photos of their selection on any webpage space, or a gallery space. | 2023-01-23 | 2023-02-23
SR0034 | Functional | Resource | The website shall allow for photos to be edited. | High | Complete | Allows website visitors to photos of the animals and may help encourage adoption | Add/Edit button should be created and added to the gallery/photo section. | Attempt to edit photos on the website. | Unit Test & User (Admins) Testing - admins can edit, or change out, photos on any webpage. | 2023-01-23 | 2023-02-23
SR0035 | Functional | Resource | The website shall allow for photos to be deleted. | High | Complete | Allows website visitors to photos of the animals and may help encourage adoption | Delete button should be created and added to the gallery/photo section. | delete five photos off the website. | Unit Test & User (Admins) Testing - admins can delete specific photos on specified webpages | 2023-01-23 | 2023-02-23
SR0036 | Functional | Resource | The website shall allow for animal information to be created. | High | Complete | Allows website visitors to get to know each animal and may help facilitate adoption | Website: Section of ready-made code that allows for admins to add information as necessary. Database: ready-made third-party database that allows for simple editing of animal records. | create a form with animal information on the website. | Unit Test & User (Admins) Testing - admins can add new animal records onto the database and website. | 2023-01-23 | 2023-04-02
SR0037 | Functional | Resource | The website shall allow for animal information to be edited. | High | Complete | Allows website visitors to get to know each animal and may help facilitate adoption | Section of ready-made code that allows for admins to edit information as necessary and easily. | edit animal information on the website. | Unit Test & User (Admins) Testing - admins can change the information of an existing record. | 2023-01-23 | 2023-04-02
SR0038 | Functional | Resource | The website shall allow for animal information to be deleted. | High | Complete | Allows website visitors to get to know each animal and may help facilitate adoption | N/A, admins can delete the outdated information in the code. | Delete animal information on the website. | Unit Test & User (Admins) Testing - admins can delete outdated animal information. | 2023-01-23 | 2023-04-02
SR0039 | Non-Functional | Performance | The payment system shall perform transactions quickly. | High | Incomplete | Allow for a quick and seamless transaction when users check out to ensure positive experience.￼ | N/A, system testing, the website should work properly and fulfill the requirements. | Attempt to quickly execute payment interactions on the website. | System testing | 2023-01-23 | N/A
SR0040 | Non-Functional | Performance | The payment system shall be user friendly. | Medium | Incomplete | Provide users with consistent access that is accessible and easy to navigate.￼ | N/A | test that the payment system is user-friendly on the website. | System testing | 2023-01-23 | N/A
SR0041 | Non-Functional | Performance | The website shall load quickly. | Medium | Complete | Provide users with constant availability and seamless usage of the website. | N/A | test and time website load time. | System testing | 2023-01-23 | 2023-02-23
SR0042 | Non-Functional | Performance | The website shall be user friendly and easily navigable. | Medium | In progress | Provide users with positive webs by website experience that allows for them to easily learn and help the organization. | N/A | Test that website is able to be navigated easily by users. | System testing | 2023-01-23 | N/A
SR0043 | Non-Functional | Performance | The payment system and website shall work together seamlessly. | High | In progress | Allow for payments to be made on the website and for it to be functional. | N/A | Test that website and payment system can work alongside alongside one another. | System testing | 2023-01-23 | N/A
SR0044 | Non-Functional | Capacity | The database shall allow for necessary storage and be scalable. | Medium | Incomplete | Have sufficient storage space for the operation of the organization. | N/A | test that the database is scalable and allows data to be collected. | System testing | 2023-01-23 | N/A
SR0045 | Non-Functional | Capacity | The website host shall provide necessary storage and be scalable. | Medium | Complete | Have sufficient storage space for the operation of the organization. | N/A | Test that website hose scalable analyze data to be collected. | System testing | 2023-01-23 | 2023-02-23
SR0046 | Non-Functional | Capacity | The website and database backups shall provide necessary storage. | Medium | Complete | Have sufficient storage space for the operation of the organization. | N/A | Test the website and back ups provide the client with necessary Storage. | System testing | 2023-01-23 | 2023-02-23
SR0047 | Non-Functional | Availability | The website shall be available and reliable with minimal downtime or interruptions | High | Complete | Provide users with constant availability and seamless usage of the website. | N/A | test that the website is reliable and has a minimal downtime or disruptions. | System testing | 2023-01-23 | 2023-02-23
SR0048 | Non-Functional | Availability | The database shall be available reliably to authorized users | High | Complete | To protect the database & information security. | N/A | Test that authorize users can access the database readily. | System testing | 2023-01-23 | 2023-02-23
SR0049 | Non-Functional | Availability | The website shall be compatible on many web browsers. | High | Complete | Provide accessibility and availability to users using different devices. | N/A | The website should be compatible with any web browsers. | System testing | 2023-01-23 | 2023-02-23
SR0050 | Non-Functional | Availability | The website shall allow for high traffic | Medium | Complete | Provide accessibility to the website by users, even at the busiest times. | N/A | test that the website can handle high amounts of traffic. | System testing | 2023-01-23 | 2023-02-23
SR0051 | Non-Functional | Availability | The website shall provide support to users through email. | Medium | Complete | Provide excellent and competent customer service. | N/A | test that uses can receive support via email. | System testing | 2023-01-23 | 2023-03-06
SR0052 | Non-Functional | Availability | The payment system shall provide support to users through email and third-party contact options. | Medium | Incomplete | Provide excellent and competent customer service. | N/A | Test at the payment system support users via email and 3rd parties. | System testing | 2023-01-23 | N/A
SR0053 | Non-Functional | Security | The website shall undergo daily backups | High | In progress | To protect data from being lost. | N/A | Test that the systems will complete daily backups. | System testing | 2023-01-23 | N/A
SR0054 | Non-Functional | Security | The website shall keep up to date with available security patches. | High | In progress | To protect website & information security. | N/A | Test that the system is up-to-date with necessary security patches. | System testing | 2023-01-23 | N/A
SR0055 | Non-Functional | Security | The website shall be monitored for outside attacks from hackers. | High | Incomplete | To protect website & information security. | N/A | Test that there is necessary, cyber security software to monitor attacks from cyber criminals. | System testing | 2023-01-23 | N/A
SR0056 | Non-Functional | Security | The website shall be scanned for malware and other viruses. | High | Incomplete | To protect website & information security. | N/A | Test that the website has frequent malware and virus scanners. | System testing | 2023-01-23 | N/A
SR0057 | Non-Functional | Security | The website shall have an SSL certificate to help keep the website secure | High | Complete | To protect website & information security. | N/A | Ensure that the website has a SSL certificate and test website security. | System testing | 2023-01-23 | 2023-02-23
SR0058 | Non-Functional | Security | The payment system shall be encrypted and secure | High | Incomplete | To protect user information from being leaked. | N/A | attempt a payment to test that is encrypted thus secure. | System testing | 2023-01-23 | N/A
SR0059 | Non-Functional | Security | The payment system shall be provided by a reliable third party. | High | In progress | To protect user information from being leaked. | N/A | Research previous third-party payment option reviews. | System testing | 2023-01-23 | N/A
SR0060 | Non-Functional | Security | The payment system shall have protected access controlled by administrators only | High | Incomplete | To protect website & information security. | N/A | Test that only administrators have access to payment systems, | System testing | 2023-01-23 | N/A
SR0061 | Non-Functional | Security | The database shall have protected access controlled by administrators only. | High | Incomplete | To protect website & information security. | N/A | Test that only the administrators have access to protected areas of website database. | System testing | 2023-01-23 | N/A
SR0062 | Non-Functional | Security | The website shall have protected access controlled by administrators only. | High | Complete | To protect website & information security. | N/A | Test that only administrators have access to protected areas on the website. | System testing | 2023-01-23 | 2023-02-23

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Supplier - On projects with multiple suppliers you may want to add a field to note the supplier responsible.
WBS ID - Add WBS ID so that the requirement can be linked to the Work Breakdown Structure and project schedule.
Test case ID - Later in the project you may want to link the requirement to the test cases that will be used to
check that the requirement meets the business objective.
This template was provided by
https://www.stakeholdermap.com/